## Sheet1
Tambola app status - ONLY COMPONENTS IMPLEMENTATION (NOT UI )
Features | status | Date | Comments
AUDIO | Not started | 2020-04-09
FIVER | DONE | 2020-04-09
HISTORY | Not started | 2020-04-09
RAING FOR THE APP | Not started | 2020-04-09
CODE CLEANING | Not started | 2020-04-10
Rotate OFF | Not started | 2020-04-10
UI handling
Feature name | status
TOP NAME | Not started
Header with buttons | Not started
Grid | Not started
Downcard | Not started
Fivers | Not started
SEEN issues
Prev number issue in automatic

## Sheet2
Commands | Use | Links
ionic cordova resources | To updathe the icon and splash images | https://ionicframework.com/docs/cli/commands/cordova-resources